## Product-Backlog
MULTI-BRANCH INVENTORY MANAGEMENT SYSTEM — PRODUCT BACKLOG REPORT
ID | AS A | I WANT TO | SO THAT | PRIORITY | SPRINT | STATUS
101 | As an Admin | I want secure login and authentication with JWT | so that only authorized users can access the system | High | 1 | Not Started
102 | As an Admin | I want to manage users and roles | so that permissions can be assigned to Admin, Manager, and Staff | High | 1 | Not Started
103 | As an Admin | I want to manage branch details | so that multiple store locations can be controlled from one system | High | 2 | Not Started
104 | As an Admin | I want to manage product catalog | so that inventory items can be added, updated, and removed | High | 2 | Not Started
105 | As an Admin | I want to manage categories and suppliers | so that products can be organized and sourced properly | Medium | 2 | Not Started
106 | As an Inventory Staff | I want to record purchase orders | so that new stock can be added to inventory | Medium | 2 | Not Started
107 | As an Inventory Staff | I want to track inventory per branch | so that stock availability can be monitored accurately | High | 3 | Not Started
108 | As a Branch Manager | I want to transfer stock between branches | so that stock shortages can be balanced | High | 4 | Not Started
109 | As a Branch Manager | I want to approve purchase orders | so that stock updates are validated before entering inventory | High | 5 | Not Started
110 | As a Cashier | I want to process sales transactions | so that inventory is reduced when products are sold | High | 5 | Not Started
111 | As a Manager | I want to receive low stock alerts | so that products can be reordered before running out | Medium | 6 | Not Started
112 | As an Admin | I want to view reports and dashboard analytics | so that business performance can be monitored | Medium | 6 | Not Started
113 | As an Admin | I want audit logs for system actions | so that all inventory changes are traceable | Medium | 6 | Not Started
114 | As a User | I want a frontend interface | so that I can interact with the inventory system easily | High | 6 | Not Started
115 | As a Developer | I want unit tests for core modules | so that system reliability is improved | Medium | 7 | Not Started
116 | As a Developer | I want CI/CD pipeline setup | so that automated builds and deployments can occur | Medium | 7 | Not Started
117 | As a System Administrator | I want the application deployed on cloud | so that users can access it online | Medium | 7 | Not Started

## Sprint-Backlog
AGILE SPRINT BACKLOG — MULTI-BRANCH INVENTORY MANAGEMENT SYSTEM
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
SPRINT 1 · Total Story Points: 13
User Story #101 - Secure Login & JWT token generation with role-based access
→ Create ASP.NET Core Web API project with Clean Architecture folders (Domain/App/Infra/API) | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Configure SQL Server connection string, EF Core DbContext, run initial migration | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
→ Implement ASP.NET Identity tables, build Register & Login APIs with JWT token | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Add [Authorize(Roles=...)] guards, test via Swagger, push to GitHub | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
User Story #102 - Admin can manage users and assign roles
→ Seed Admin, Branch Manager, Staff roles in DB on application startup | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Build Get All Users API and Assign Role to User API (Admin only) | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Build Deactivate User (soft delete) API, write unit test for role logic | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1
SPRINT 2 · Total Story Points: 19
User Story #103 - Admin can create, edit, view and soft-delete branches
→ Create Branch entity: Name, Address, ManagerName, Contact, IsActive fields | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Build GET/POST/PUT/DELETE branch endpoints with unique name validation | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
→ Implement soft delete — IsActive flag, inactive branches hidden from reports | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 0 | 0 | 0 | 0
User Story #104 - Admin can manage products with unique SKU and reorder levels
→ Create Product entity: SKU (unique), Name, Price, ReorderLevel, CategoryId, SupplierId | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Build full CRUD APIs for Products with Swagger XML documentation | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
→ Enforce SKU uniqueness — return 400 on duplicate, FluentValidation for Price > 0 | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
→ Apply role-based access — only Admin can create/delete products | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
User Story #105 - Admin can manage product categories
→ Create Category entity and full CRUD API endpoints | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Link Category as FK to Product, test relationship and push Sprint 2 to GitHub | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1
User Story #106 - Admin can manage suppliers linked to products
→ Create Supplier entity and full CRUD API endpoints | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Link Supplier as FK to Product and PurchaseOrder tables | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1
SPRINT 3 · Total Story Points: 13
User Story #107 - Branch-wise real-time stock tracking with concurrency control
→ Create Inventory entity: BranchId, ProductId, QuantityAvailable, RowVersion, LastUpdated | 3 | Indresh Mehta | To Do | 3 | 3 | 0 | 0 | 0 | 0 | 0
→ Build GET /inventory?branchId= — role-filtered (manager sees own branch only) | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 1 | 0 | 0 | 0
→ Build Add/Update stock API with guard clause preventing negative quantity | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 3 | 3 | 0 | 0
→ Implement RowVersion concurrency token — handle DbUpdateConcurrencyException | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Write xUnit tests for stock update and negative stock edge cases, push Sprint 3 to GitHub | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
SPRINT 4 · Total Story Points: 13
User Story #108 - Atomic stock transfer between branches with transaction rollback & logs
→ Design StockTransfer and TransferItems tables with FK to Inventory | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Build POST /transfers API — validate source branch has sufficient stock before transfer | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 0 | 0 | 0 | 0
→ Implement EF Core BeginTransactionAsync — atomic deduct from source + add to destination | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 3 | 1 | 0 | 0
→ Add rollback in catch block — transaction rolls back entirely on any failure | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 0
→ Build GET /transfers — Admin sees all, Manager sees own branch, write xUnit tests | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
SPRINT 5 · Total Story Points: 16
User Story #109 - Manager creates purchase orders, Admin approves to auto-update stock
→ Create PurchaseOrder & PurchaseItems tables with FK to Supplier and Product | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Build POST /purchase-orders — create PO with Pending status | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
→ Build PUT /purchase-orders/{id}/approve — auto-increment stock, Admin role only | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Test full PO approval flow end-to-end and verify stock increment | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
User Story #110 - Staff records a sale, stock auto-deducted, invoice record created
→ Create Sales and SaleItems tables with FK to Branch and Product | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
→ Build POST /sales — validate stock available → deduct → create invoice record | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 0
→ Return sale summary (product, qty, price, total) in API response | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ End-to-end test: PO → Inventory → Sale full lifecycle, push Sprint 5 to GitHub | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1
SPRINT 6 · Total Story Points: 31
User Story #111 - System alerts manager when stock falls below reorder level
→ Build LowStockService: LINQ query where QuantityAvailable < ReorderLevel | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Expose GET /inventory/low-stock endpoint | 1 | Indresh Mehta | To Do | 1 | 1 | 0 | 0 | 0 | 0 | 0
→ Display low stock items with alert badge on React dashboard | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
User Story #112 - Admin views analytics dashboard with branch stock values and sales reports
→ Build GET /dashboard — stock value per branch using LINQ GroupBy + Sum | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
→ Build GET /reports/sales?month=&year= monthly sales report API | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Build GET /reports/top-products — top 5 selling products | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Display analytics on React Dashboard page with Chart.js bar/line charts | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
User Story #113 - Admin can trace every stock change with full audit trail
→ Create AuditLog entity: UserId, BranchId, ProductId, Action, Timestamp | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
→ Implement ActionFilter to auto-log every stock change | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Build GET /audit-logs endpoint (Admin only), verify logs in Swagger | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 0
User Story #114 - Responsive React frontend consuming all backend APIs with JWT auth
→ Setup React app with React Router, Axios, Context API for JWT auth state | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
→ Build Login page — call POST /auth/login, store JWT in Context, redirect by role | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Build Dashboard page — stock values per branch, low stock alert badges | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Build Inventory & Stock Transfer pages — view stock, submit transfer form | 3 | Indresh Mehta | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3
→ Build Sales page — record sale form, show invoice summary on submit | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Build Reports page — monthly sales Chart.js charts, implement Protected Routes | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
SPRINT 7 · Total Story Points: 18
User Story #115 - Developer writes unit and integration tests for all critical business logic
→ Write xUnit tests for stock deduction logic — positive & negative quantity cases | 2 | Indresh Mehta | To Do | 2 | 2 | 0 | 0 | 0 | 0 | 0
→ Write xUnit tests for transfer validation — sufficient & insufficient stock cases | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 0 | 0 | 0 | 0
→ Write xUnit tests for low stock alert trigger (qty < reorder level) | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 0 | 0 | 0
→ Write integration tests for Login, Inventory, Transfer APIs via WebApplicationFactory | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
User Story #116 - Azure DevOps CI/CD pipeline auto-builds and tests on every push
→ Create azure-pipelines.yml with build and test stages | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 0 | 0
→ Configure pipeline trigger on push to main branch | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 0
→ Add test task in pipeline — failed tests block deployment, verify pipeline dashboard | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 0
User Story #117 - System is deployed live on Azure App Service with Azure SQL
→ Deploy ASP.NET Core Web API to Azure App Service | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Configure Azure SQL Database, run EF Core migrations in production | 2 | Indresh Mehta | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
→ Verify Swagger on live URL, update GitHub README with link, final submission | 1 | Indresh Mehta | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1

## User story
MULTI-BRANCH INVENTORY MANAGEMENT SYSTEM — User Stories
S.NO | User Story | Acceptance Criteria | Sprint
1 | As a Admin, I want to register an account and log in securely using my credentials so that my identity is verified and I receive a JWT token for system access. So that only authenticated users can access the system and each user gets appropriate role-based access. | • The system must accept valid email and password for login. • On successful login, a JWT Bearer token must be returned. • Token must include the user's role (Admin / Branch Manager / Staff). • Invalid credentials must return HTTP 401 Unauthorized. • Password must be hashed — never stored as plain text. • All protected API endpoints must reject requests without a valid JWT. | Sprint 1
2 | As a Admin, I want to create user accounts, assign roles (Admin / Branch Manager / Staff) and deactivate users when needed. So that only authorized personnel have access and permissions are properly controlled across the system. | • Admin must be able to create a new user with name, email, password and role. • Admin must be able to assign or change the role of any user. • Admin must be able to soft-delete (deactivate) a user — data is preserved. • Deactivated users must not be able to log in. • The system must enforce that only Admins can access the user management API. • All user management actions must be logged in the Audit Log. | Sprint 1
3 | As a Admin, I want to add, edit, view and soft-delete branches with their address, manager and contact details. So that multiple store locations can be independently tracked and managed within the system. | • Branch name must be unique — duplicate names must return HTTP 400. • Each branch must store: Name, Address, Manager Name, Contact Number, IsActive flag. • Admin can deactivate a branch (soft delete) — data and stock history are preserved. • Inactive branches must not appear in inventory or sales dropdowns. • Branch Manager can only view their own assigned branch data. • All branch changes must be reflected immediately in the inventory module. | Sprint 2
4 | As a Admin, I want to add, edit and manage products with a unique SKU, price, category, reorder level and supplier link. So that every product in the system is uniquely identifiable and ready for inventory tracking across all branches. | • SKU must be unique across the entire system — duplicate SKU returns HTTP 400. • Mandatory fields: SKU, Product Name, Price (> 0), Reorder Level (> 0), Category, Supplier. • Product must be linked to a valid Category and Supplier via foreign keys. • Admin can soft-delete a product — IsActive = false, product hidden from sales forms. • FluentValidation must enforce all field rules server-side. • Only Admin role can create, update or delete products. | Sprint 2
5 | As a Admin, I want to create and manage product categories so that products are logically grouped and easy to filter. So that inventory reports and product searches can be filtered by category across all branches. | • Admin can create, edit and delete categories. • Category name must be unique. • Deleting a category with linked products must return a validation error — no orphan products. • Category list must be available as a dropdown when creating/editing products. • Category must be displayed in product listings and inventory views. | Sprint 2
6 | As a Admin, I want to add and manage suppliers so that each product and purchase order is linked to a verified supplier. So that purchase orders can be created with valid supplier references and procurement is traceable. | • Admin can create, edit and delete supplier records. • Supplier must include: Name, Contact Person, Phone, Email, Address. • A supplier cannot be deleted if it has linked products or purchase orders — return HTTP 400. • Supplier list must appear as a dropdown when creating products and purchase orders. • Supplier data must be visible in purchase order history. | Sprint 2
7 | As a Branch Manager, I want to view real-time stock levels for my branch and update quantities, with the system preventing negative stock and handling simultaneous updates safely. So that inventory counts are always accurate, no branch ever goes into negative stock, and concurrent updates do not cause data corruption. | • Each branch must have its own independent inventory record per product. • Branch Manager can only view and update inventory of their own branch. • Admin can view inventory of all branches. • Stock update must be rejected if it would result in quantity below zero — return HTTP 400. • The Inventory table must use a RowVersion (Timestamp) column for optimistic concurrency. • If two users update the same stock simultaneously, a DbUpdateConcurrencyException must be caught and handled gracefully. • Every stock change must be recorded in the Audit Log with user, branch, product and timestamp. • LastUpdated field must be auto-set on every inventory change. | Sprint 3
8 | As a Branch Manager, I want to request a stock transfer from one branch to another, with the system validating stock availability and ensuring the operation is atomic — either fully completed or fully rolled back. So that branches can rebalance inventory without risk of data inconsistency or partial transfers. | • Branch Manager can submit a transfer request specifying: Source Branch, Destination Branch, Product, Quantity. • System must verify source branch has sufficient stock before processing — return HTTP 400 if not. • The entire transfer (deduct from source + add to destination) must execute inside a single EF Core database transaction. • If any step fails, the entire transaction must roll back — no partial updates. • A TransferLog record must be created with: source branch, destination branch, product, quantity, initiated by, timestamp. • Admin can view all transfer logs; Branch Manager can view only transfers involving their branch. • xUnit tests must cover: successful transfer, insufficient stock rejection, and transaction rollback scenarios. | Sprint 4
9 | As a Branch Manager, I want to create purchase orders from suppliers and have the Admin approve them so that branch stock is automatically incremented upon approval. So that the procurement process is tracked end-to-end and stock increases only after a verified approval. | • Branch Manager can create a Purchase Order by selecting: Supplier, Products, Quantities. • New PO must be saved with status: Pending. • Admin can view all pending POs and approve or reject them. • On approval, the system must automatically increment the relevant branch inventory. • PO status must update to Approved and the approval timestamp must be recorded. • Rejected POs must not affect inventory. • PO history must be viewable with full product and quantity details. | Sprint 5
10 | As a Staff, I want to record a sale for a branch by selecting a product and quantity, with the system validating available stock, deducting it automatically and generating an invoice record. So that every sale is accurately captured, stock levels are always up to date and invoices are stored for reference. | • Staff must select: Branch, Product, Quantity to record a sale. • System must validate that sufficient stock exists before processing — return HTTP 400 if not. • On successful sale, stock must be deducted from the correct branch inventory. • A Sale record must be created with: Branch, Product, Quantity, Unit Price, Total Amount, Date. • SaleItems table must store individual line items. • The API response must return a sale summary (product, qty, price, total). • Stock deduction and sale creation must be atomic — no partial saves. | Sprint 5
11 | As a Branch Manager, I want the system to automatically detect when any product's stock falls below its reorder level and display an alert on my dashboard. So that I can reorder stock proactively and avoid running out of products at my branch. | • The system must compare QuantityAvailable against ReorderLevel for every product in every branch. • Any product where QuantityAvailable < ReorderLevel must be flagged as low stock. • Low stock items must be visible on the Branch Manager's dashboard with a clear alert badge. • Admin must see low stock alerts for all branches. • The GET /inventory/low-stock API endpoint must return a list of low stock items with branch, product and current quantity. • Alerts must update in real time when stock is replenished above the reorder level. | Sprint 6
12 | As a Admin, I want a dashboard showing total stock value per branch, top-selling products, monthly sales figures and low stock summaries visualized as charts. So that I can monitor business performance and make informed inventory and procurement decisions. | • Dashboard must display: total stock value per branch (Qty × Price) using LINQ GroupBy + Sum. • Top 5 best-selling products must be listed with total units sold. • Monthly sales report must be filterable by month and year. • All analytics must be available via dedicated API endpoints. • React frontend must display bar/line charts using Chart.js. • Admin sees data for all branches; Branch Manager sees only their branch data. • Dashboard data must load within 3 seconds for up to 10 branches. | Sprint 6
13 | As a Admin, I want every stock change, transfer, sale and purchase order to be automatically logged with the user, branch, product and timestamp so that all actions are fully traceable. So that any discrepancy in inventory can be investigated and accountability is maintained across all users. | • Every stock add, update, transfer, sale and PO approval must create an AuditLog entry automatically. • Each log entry must capture: UserId, UserName, BranchId, ProductId, Action Type, Old Value, New Value, Timestamp. • Logging must be implemented via an ASP.NET Core ActionFilter — not manually in each controller. • Admin can view all audit logs via GET /audit-logs with optional filters by branch, product and date range. • Audit logs must be read-only — no user should be able to edit or delete them. • Logs must be stored permanently in the AuditLogs table. | Sprint 6
14 | As a All Users, I want a responsive React frontend with role-based pages for Login, Dashboard, Inventory, Stock Transfer, Sales and Reports that connects to all backend APIs using JWT authentication. So that all system features are accessible through a clean, browser-based UI without needing to use Swagger or Postman. | • React app must use React Router for page navigation. • JWT token must be stored in Context API and attached to all Axios API calls as Bearer token. • Login page: email/password form calling POST /auth/login, redirect by role after success. • Dashboard: branch stock values, low stock alert badges, top products summary. • Inventory page: view stock per branch, update stock quantity form. • Stock Transfer page: form to select source/destination branch and product with quantity. • Sales page: record sale form, display invoice summary after submission. • Reports page: monthly sales Chart.js line chart with month/year filter. • Protected Routes: unauthenticated users redirected to Login page. • Branch Manager can only see their own branch data on all pages. | Sprint 6
15 | As a Developer, I want to write xUnit unit tests and integration tests covering all critical business logic so that the system's reliability is verified before deployment. So that bugs in stock management, transfers and alerts are caught automatically in the CI/CD pipeline before reaching production. | • xUnit tests must cover: stock deduction (positive and negative quantity cases). • xUnit tests must cover: transfer validation (sufficient and insufficient stock scenarios). • xUnit tests must cover: low stock alert trigger (QuantityAvailable < ReorderLevel). • Integration tests must cover: Login API, Inventory API, Transfer API using WebApplicationFactory. • All tests must use Moq for dependency mocking and EF Core InMemory for DB. • Minimum 80% code coverage on all service-layer business logic. • All tests must pass before the CI/CD pipeline allows deployment. | Sprint 7
16 | As a Developer, I want an Azure DevOps CI/CD pipeline that automatically builds the project and runs all tests on every push to the main branch. So that code quality is enforced continuously and broken builds never reach the production environment. | • An azure-pipelines.yml file must define the full pipeline with build and test stages. • Pipeline must trigger automatically on every push or pull request to the main branch. • The build stage must restore NuGet packages and compile the solution. • The test stage must run all xUnit tests and publish a test results report. • A failed test must block the pipeline — deployment must not proceed. • Pipeline status badge must be visible on the GitHub repository README. • Build and test results must be visible on the Azure DevOps Pipelines dashboard. | Sprint 7
17 | As a Admin, I want the system deployed to Azure App Service connected to Azure SQL Database so that it is accessible live via a public URL. So that the project is production-ready, accessible to all stakeholders and demonstrates real cloud deployment skills. | • ASP.NET Core Web API must be deployed to Azure App Service using Azure DevOps pipeline. • Azure SQL Database must be configured and EF Core migrations must run on deployment. • Swagger UI must be accessible at the live Azure URL for API testing. • Connection strings must be stored in Azure App Service environment variables — not in code. • The live URL must be added to the GitHub repository README. • The deployment must be triggered automatically by the CI/CD pipeline on successful build + test. • System must be fully functional end-to-end on the live Azure environment. | Sprint 7